## OnSiteConsoleX
Schedule | ✓
Messages | ✓
Payroll | ✓
Reports | ✓
review | ✓
edit | ✓
DPS | 95% | need to be able to save calculation variables
_co.dpsSettingsCancel
global.addEventListener
Invoice | 90% | fix KN output
Templates | ✓
Pre-Auth
request | ✓
Processed | ?? | need to parse PDF…
reports | ✓
App
Build | 90% | Still a couple of errors…
Test | 0%

## OnSiteConsoleX-Detail
Notes | Expanded | Completed | Changed
Implement a web (cloud) based system which would: log work orders (employee hours, client information, materials billing), invoice customers, and update accounting and payroll without a need for manual data re-entry from hardcopy.
SCOPE OF SERVICES
Project Overview
1. Update current website to a modern/professional look
2. Create interlinking forms and database services to eliminate manual data re-entry
3. Eliminate hardcopy and move invoice and documents to external redundant cloud based backup service
4. Provide a mobile app based using PhoneGap for remote employee work log entry with offline/online data synchronization
Establish functional database:
1. main interface for data flow:
* Work order
* invoicing
* reporting
* Customer records
* Employee records
* Parts/materials records
2. Output function: PDF creation
A smartphone based application
1. Password protected employee login (Unique employee identifier)
* SPECIFY: option to bypass password protection if phone lock is enabled is my recommendation
Data fields:
1. Geolocation stamping (not visible in app UI)
1. Stamped upon work order creation
2. logged in 15 minute increments
3. Log is stopped when ticket flag state is changed (Review/Specify work order states)
* Open -in progress
* Open -paused (end of shift)
* Open -Pending parts/fluids availability
* Closed -submitted complete
4. Geolocation stamp sorts potential customer by radius to location when a work order is created, customer selection is via dropdown in order of distance from geostamp (closest, next closest, next next closest, and specify)
* This option can only be implemented if customer locations are obtainable through current records. Otherwise this feature is outside the scope of this project and not included in the estimate, but can be added in the future.
2. Date:
3. Company:
4. Unit Number
5. Work Order number
6. Time in/out (up to 12 entries or specify other maximum)
7. Notes: (Please specify character length if other than 400)
8. English and Spanish user interface (UI)
9. Additional selection for job type
* Fluid Toppers (Indicate what data changes with this selection)
* Mechanics
10. list or search feature based on employee login
11. Manager credentials accesses own and subordinate work orders
* Admin credentials accesses all data through database -not app
A redesigned website:
1. Modern/professional look
2. Content management
3. News
4. Content Editing
5. Home
6. About Us
7. Blog (Features must be defined)
8. Customer/Services overview
9. Contact
10. FAQ
11. Employee/Customer login
12. Administration, User Management, User profiles
13. Form interface for database input/editing
14. Employee Administration (Add/edit/delete employees, Password management, user profiles)
Project Implementation
Upon completion of this project, and final payment, S.E.S.A. Fleet services will entirely own all rights to the entire, *compiled*, software suite, with the following exceptions:
1. Original Source Code (S.E.S.A. Fleet services has the right to modify and reuse any and all programs in any way you see fit, and upon request I will provide the entire source code, but parts of the code may be under copyright through another programming entity)
2. I retain the rights to reuse any and all algorithms and libraries which built the source code, which can be reused in future projects
3. Any previously copyrighted 3rd party software packages or code used in the creation of your software is governed by their copyright and must be used in accordance to their copyright agreement
4. If registering a domain name, hosting service, storage service etc. is required for completion of the project that, will be relinquished or transferred to S.E.S.A. Fleet services who will become completely responsible for all decisions regarding the payments, maintenance and continuation of those services.
Training:
1 Provide up to three days onsite for implementation.
* Because this program automates existing processes rather than create new ones, very little training will be needed to gain maximum benefit. The goal of training is to deliver the software to you with all the knowledge needed to incorporate this into your standard operating procedures.
2. Scope of training:
* Expressly limited to Tino and Chris Vela
* Potentially confidential company information (accounting procedures, datacollection, billing etc.) will be disclosed
* Field training will be implemented by you through management and SOP's.
* Field personnel will follow current workflows, but through an Android/iPhone application interface.
* Telephone/Email support for the two weeks following implementation.
* Software Bugs, *defined as programming errors made by my team* will be corrected in as timely a matter as possible.
- Must be alerted to me by telephone
- Bug reports will be submitted by email or some agreed upon traceable electronic submission.
- Bug reports can be submitted during the 6 months following live implementation.
Project review points
1. Design review for website
2. Work log form design review
3. eForm invoicing review
4. Periodic progress review meetings during several stages. (30-45 minute maximum, with prepared agenda)
5. Pre-live testing of all software modules
YOUR RESPONSIBILITIES
This project will demand your active participation in several areas, and me, and or, my team will need your dedication in this to ensure timely project completion.
1. Provide complete concise specifications for the project. (Review the section “Specifications” to ensure all needs will be met; submit any additions before project commencement).
2. Provide information as needed on processes and control points.
3. Provide Parts and Services data for database entry (Electronic format .CSV, .XLSX, .DOCX)
4. Provide Customer billing/contact information for database entry (Electronic format .CSV, .XLSX, .DOCX)
5. Review and report back on design ideas
6. Provide access to accounting interface for import testing and data integrity
7. Participate in live trials prior to implementation.
8. Provide candid feedback during or within 24 hours of a progress review meetings
Final Notes
Professional Services
Travel (Within the state of TX):
1. Emergency travel requested less than 8 calendar days prior to desired travel date: \$1,500
2. Priority travel requested at least 8 calendar days prior to travel date: \$1,000
3. Non priority travel requested 22 calendar days prior to travel date: \$600
Rates:
1. Professional Services \$90/hr. billed in 4 hour blocks while traveling Per Diem (Hidalgo County):
* Hotel (Govt. Per Diem Rates) \$88
* Meals (Govt. Per Diem Rates) \$56

## OnSiteXI
OnSiteXI
Add Crew Number for KN
CrewNo. Replaces WONo.
Add incomplete Reports tab
reports without Unit No., or WO No. are persisted until completed (this does not affect hours for payroll, since the report exists -only that the user will know that it is still incomplete)
Add Manager Mode
Schedule summary, detail view, summary and detail per site;
We can add other features as well -suggestions?
Add Timesheet Capture and storage
Halliburton sites: Techs can capture/upload timesheets
Badges: awards
Badges and awards to show up on user home-screen (increase morale, allow managers to give awards for outstanding accomplishments… lots of ideas
Primary Badge (Tech Class) displayed on Home Screen
Batch work-order entry mode
Add multiple WO's, Units, Notes, time on one screen
Perhaps set this as “Advanced Mode” Option
Entire shift can be entered on a single screen much like the old website
Not limited to 9 WO’s/Units
“+” button to add additional WO for that day
Entire Shift can also be edited with the same UI (where work order number or other details might need to be added later…
Can set hours for a repeated task for several units
Ex: 6 units with the same task performed, time set for the entire group
Time is divided by unit (this works out better, since individual reports are limited to 30 minute increments and a short task repeated for several units might only require 15-20 minutes per vehicle.
Check-stub summary tab
Shows actual payroll detail after payroll is run (export summary report from QuickBooks); this way the techs shouldn't need to come to the office to copy pay stubs
Details for deductions etc. can be configured in OnSiteConsoleXI
Possibly some configurations editable by employee (synced to DB)
Exportable report for manually updating QuickBooks on changes from Employee
Enhanced Profile
Add avatar or image,
Edit phone number,
Edit Address,
Edit Preferences…
In-app Messaging
Msg other techs, managers, site-mates etc. Useful to reply to mgmt. msgs, report safety issues, request sick day…
Messaging extended to OnSiteConsoleXI:
Automatic Groups –Worksite groups are automatically generated from schedule,
Msg to individual or group
Typical chat interface:
Txt msgs at first;
Full MMS TBD;
History and DB TBD…
Missed Hours and Reimbursements
Reports for missed hours: include fields for number of hours, dates of missed hours, description, … reimbursements: description, Date, amount, image capture of receipt… other fields TBD
Payroll summary detailed
add deductions and estimated take-home pay instead of just raw hours
Performance optimizations
App queries current and previous payroll period DB's plus incomplete reports DB(s) other optimizations to improve performance... Reports DB by week: create a new reports DB for each payroll period. DB name is "reports" + excel payroll period date number; ex: reports43068
Preferences stored per user, online
Update how user preferences are stored and retrieved; editable fields etc. This needs a bit of an overhaul for consistency and accuracy across the app and console
Stats page
Awards/badges, time-in-service, consecutive days worked, hours worked by week/month/year… perhaps some other statistics that the techs might like to see
UI Themes
Dark/Light, perhaps color options as well; themes for OnSite UI
Update home screen UI
change shift summary look/feel
Update Reports UI
cleaner UI; eliminate unused UI elements; change some graphics; improve look and responsiveness
Automatic Lunch Break added to shifts
- converts start/end times to account for this break in the day
Vacation/Time off Requests
Add Time Off request page; track vacation/time off requests through App and Console Time Off Approval/Denial + manager comments viewable; resubmit/Date change suggestions can be tracked
Update geolocation functionality
Phone usage is discouraged at many sites and "app" usage even if legitimate may be suspect by client.
Compliance enforcement is also an issue.
Currently we are still only in the 95%-98% in getting reports in before payroll. It is fruitless to add another requirement which can be ignored...
Currently: Geoloc is superfluous. Techs typically do not access the app during shift hours
Geo-stamping can only happen when the app is accessed.
If App is used at the hotel, then no useful information is gathered.
GEOLOCATION DISCUSSION
It is not legal to force geotracking on personal devices (could only be enforced on company issued devices...)
Possible options: require image capture of UnitNo: geostamp is recorded on unit.
We should still clear this with the clients so that our techs are not hassled for using their phone
Clear this with clients so that they understand the reason and purpose of photographing the unit numbers
Alternately, WorkOrder image capture with geostamp...
again clear with clients (see above)
Usefulness of geotagging is not in question
Automatic Travel Reports
WorkSite Verification
Tech Location Verification
Shift Verification
Voluntary compliance is the only legal way to gather this data without issuing mobile devices or a legally vetted employment contract which explicitly states geotagging requirements and compliance and usage guidelines.
Other Points for Discussion
With or without Geolocation enhancements, we need to focus on scheduling accuracy with OnSiteConsoleX/XI
Particularly, Shifts (AM/PM) for billing Brownfield or any other worksites invoiced by shift
Payroll: Premium hours calculation (when Tech works part of the week at SESA)